## jira_200_rows
Issue_ID | Project | Summary | Issue_Type | Priority | Status | Assignee | Reporter | Created_Date | Resolved_Date | Story_Points | Components | Labels | Epic_Link | Sprint | Comments_Count | Time_Spent_Hours
PROJ-C-1001 | PROJ-C | Bug - login issue 1 | Bug | High | To Do | Carlos | Reporter1 | 2025-07-12 | 2025-08-08 |  | UI |  |  | Sprint 4 | 11 | 51.99
PROJ-C-1002 | PROJ-C | Task - API issue 2 | Task | Medium | To Do | Alice | Reporter2 | 2025-03-08 | 2025-03-17 | 3 | UI |  | EPIC-12 | Sprint 1 | 11 | 36.75
PROJ-A-1003 | PROJ-A | Sub-task - payment issue 3 | Sub-task | Medium | In Review | Unassigned | Reporter5 | 2025-01-05 |  |  | UI | backend |  |  | 6 | 22.24
PROJ-C-1004 | PROJ-C | Improvement - dashboard issue 4 | Improvement | Medium | In Progress | Unassigned | Reporter3 | 2024-03-14 |  | 8 | Docs | security | EPIC-30 | Sprint 9 | 3 | 54.77
PROJ-A-1005 | PROJ-A | Bug - export issue 5 | Bug | Lowest | In Progress | Emma | Reporter1 | 2024-08-04 |  |  | Backend | research | EPIC-5 | Sprint 9 | 8 | 21.02
PROJ-C-1006 | PROJ-C | Task - payment issue 6 | Task | Medium | In Progress | Carlos | Reporter5 | 2025-05-20 | 2025-05-23 | 2 | Docs | security,refactor | EPIC-13 | Sprint 8 | 8 | 20.11
PROJ-C-1007 | PROJ-C | Improvement - export issue 7 | Improvement | Lowest | Done | Unassigned | Reporter5 | 2024-09-30 | 2024-11-18 | 1 | API | frontend |  |  | 4 | 77.75
PROJ-A-1008 | PROJ-A | Story - dashboard issue 8 | Story | Low | In Review | Unassigned | Reporter5 | 2024-07-22 | 2024-09-08 | 8 | CI/CD |  |  | Sprint 8 | 0 | 8.95
PROJ-B-1009 | PROJ-B | Improvement - payment issue 9 | Improvement | High | In Progress | Alice | Reporter2 | 2025-08-03 |  | 13 | DB |  |  | Sprint 3 | 2 | 52.78
PROJ-C-1010 | PROJ-C | Bug - import issue 10 | Bug | Medium | In Review | Divya | Reporter5 | 2024-07-24 |  |  | Docs | research | EPIC-8 | Sprint 1 | 9 | 44.31
PROJ-C-1011 | PROJ-C | Bug - payment issue 11 | Bug | Low | In Review | Divya | Reporter1 | 2024-02-02 |  |  | Integration | research,backend |  |  | 9 | 46.1
PROJ-A-1012 | PROJ-A | Epic - login issue 12 | Epic | High | To Do | Bob | Reporter4 | 2024-12-28 | 2025-01-26 |  | Docs | backend,frontend |  | Sprint 6 | 12 | 68.93
PROJ-A-1013 | PROJ-A | Bug - payment issue 13 | Bug | Medium | To Do | Carlos | Reporter3 | 2025-04-18 | 2025-06-16 |  | DB |  |  | Sprint 11 | 8 | 66.88
PROJ-A-1014 | PROJ-A | Sub-task - login issue 14 | Sub-task | High | To Do | Hiro | Reporter4 | 2024-08-06 |  |  | Backend | refactor |  |  | 4 | 33.84
PROJ-C-1015 | PROJ-C | Sub-task - login issue 15 | Sub-task | Medium | Done | Carlos | Reporter2 | 2024-10-30 | 2024-11-12 |  | Integration |  | EPIC-11 | Sprint 10 | 7 | 40.23
PROJ-C-1016 | PROJ-C | Bug - API issue 16 | Bug | Highest | To Do | Carlos | Reporter1 | 2024-03-10 |  |  | DB | release,refactor |  | Sprint 7 | 10 | 46.69
PROJ-C-1017 | PROJ-C | Task - sync issue 17 | Task | Medium | In Review | Fahad | Reporter2 | 2024-09-28 | 2024-11-09 | 5 | API |  |  | Sprint 10 | 9 | 79.69
PROJ-A-1018 | PROJ-A | Story - performance issue 18 | Story | Medium | To Do | Fahad | Reporter1 | 2024-09-07 | 2024-09-17 | 8 | Docs | frontend,performance |  | Sprint 11 | 1 | 75.11
PROJ-A-1019 | PROJ-A | Task - API issue 19 | Task | High | Done | Carlos | Reporter3 | 2024-10-15 | 2024-11-22 | 13 | API | refactor,research |  |  | 0 | 7.38
PROJ-B-1020 | PROJ-B | Improvement - import issue 20 | Improvement | Lowest | In Progress | Carlos | Reporter3 | 2024-06-14 |  | 8 | UI | hotfix,refactor | EPIC-12 | Sprint 3 | 6 | 10.2
PROJ-B-1021 | PROJ-B | Task - payment issue 21 | Task | Highest | Reopened | Alice | Reporter3 | 2024-08-03 |  | 3 | CI/CD | hotfix |  | Sprint 3 | 12 | 64.86
PROJ-B-1022 | PROJ-B | Bug - payment issue 22 | Bug | High | In Progress | Gita | Reporter2 | 2024-09-30 | 2024-11-13 |  | DB |  |  | Sprint 8 | 5 | 24.42
PROJ-A-1023 | PROJ-A | Bug - import issue 23 | Bug | High | In Progress | Emma | Reporter1 | 2024-10-12 | 2024-11-13 |  | Docs |  |  |  | 1 | 70.16
PROJ-B-1024 | PROJ-B | Bug - export issue 24 | Bug | Highest | To Do | Bob | Reporter5 | 2025-03-20 | 2025-05-09 |  | DB | backend,release |  | Sprint 1 | 11 | 34.88
PROJ-C-1025 | PROJ-C | Sub-task - payment issue 25 | Sub-task | Medium | Done | Unassigned | Reporter2 | 2025-01-07 | 2025-02-03 |  | Docs |  |  | Sprint 2 | 11 | 72
PROJ-C-1026 | PROJ-C | Task - import issue 26 | Task | Medium | In Progress | Emma | Reporter5 | 2024-05-10 | 2024-06-21 | 13 | Docs |  |  | Sprint 9 | 0 | 24.31
PROJ-A-1027 | PROJ-A | Task - performance issue 27 | Task | Medium | In Review | Hiro | Reporter4 | 2025-03-28 |  | 13 | Backend | performance | EPIC-25 | Sprint 5 | 3 | 64.53
PROJ-A-1028 | PROJ-A | Bug - API issue 28 | Bug | Medium | In Progress | Bob | Reporter4 | 2025-02-28 |  |  | Docs | security | EPIC-21 | Sprint 2 | 12 | 34.01
PROJ-A-1029 | PROJ-A | Improvement - performance issue 29 | Improvement | High | In Progress | Isha | Reporter2 | 2024-05-04 | 2024-06-24 | 13 | Integration |  |  |  | 7 | 49.01
PROJ-C-1030 | PROJ-C | Improvement - API issue 30 | Improvement | Medium | Blocked | Hiro | Reporter2 | 2025-05-01 | 2025-06-18 | 13 | API |  |  | Sprint 5 | 7 | 6.2
PROJ-B-1031 | PROJ-B | Bug - import issue 31 | Bug | Medium | Done | Bob | Reporter2 | 2024-06-03 | 2024-06-17 |  | Docs |  | EPIC-14 | Sprint 8 | 6 | 4.98
PROJ-B-1032 | PROJ-B | Task - export issue 32 | Task | High | Blocked | Alice | Reporter5 | 2025-01-24 | 2025-03-25 | 3 | CI/CD | release |  | Sprint 8 | 0 | 31.11
PROJ-C-1033 | PROJ-C | Story - login issue 33 | Story | Medium | To Do | Hiro | Reporter2 | 2025-06-30 | 2025-07-25 | 1 | Docs | hotfix | EPIC-13 | Sprint 8 | 5 | 27
PROJ-B-1034 | PROJ-B | Task - login issue 34 | Task | Highest | In Progress | Bob | Reporter4 | 2024-01-20 |  | 3 | Backend | frontend,security | EPIC-8 | Sprint 1 | 9 | 12.19
PROJ-A-1035 | PROJ-A | Story - payment issue 35 | Story | Low | Blocked | Hiro | Reporter3 | 2025-01-12 | 2025-02-19 | 2 | API |  |  | Sprint 7 | 6 | 75.32
PROJ-A-1036 | PROJ-A | Bug - login issue 36 | Bug | High | In Review | Bob | Reporter3 | 2024-05-03 |  |  | API | performance,frontend |  | Sprint 7 | 7 | 8.44
PROJ-B-1037 | PROJ-B | Story - sync issue 37 | Story | High | Done | Gita | Reporter2 | 2025-06-18 | 2025-07-29 | 8 | CI/CD |  |  | Sprint 12 | 9 | 21.47
PROJ-A-1038 | PROJ-A | Improvement - import issue 38 | Improvement | Low | Done | Divya | Reporter4 | 2025-08-06 | 2025-09-14 | 3 | UI | hotfix |  | Sprint 5 | 5 | 22.37
PROJ-C-1039 | PROJ-C | Story - performance issue 39 | Story | Medium | To Do | Divya | Reporter1 | 2024-09-04 |  | 8 | CI/CD | research |  | Sprint 5 | 3 | 32.35
PROJ-A-1040 | PROJ-A | Task - export issue 40 | Task | Medium | In Progress | Isha | Reporter3 | 2025-03-11 |  | 3 | Docs | refactor | EPIC-24 | Sprint 2 | 11 | 42.87
PROJ-C-1041 | PROJ-C | Bug - API issue 41 | Bug | Medium | In Progress | Jatin | Reporter5 | 2024-10-16 |  |  | API |  | EPIC-23 | Sprint 5 | 0 | 77.94
PROJ-C-1042 | PROJ-C | Task - performance issue 42 | Task | Highest | In Review | Hiro | Reporter1 | 2024-01-13 |  | 5 | DB |  | EPIC-28 | Sprint 2 | 6 | 39.34
PROJ-C-1043 | PROJ-C | Story - payment issue 43 | Story | Low | To Do | Jatin | Reporter3 | 2024-03-28 |  | 8 | CI/CD | release,security |  | Sprint 8 | 4 | 68.81
PROJ-B-1044 | PROJ-B | Task - dashboard issue 44 | Task | High | In Review | Bob | Reporter2 | 2024-08-04 | 2024-08-09 | 2 | Backend |  | EPIC-15 | Sprint 8 | 4 | 2.61
PROJ-B-1045 | PROJ-B | Story - API issue 45 | Story | High | In Progress | Unassigned | Reporter2 | 2024-09-27 |  | 5 | UI | hotfix,research |  | Sprint 3 | 12 | 24.61
PROJ-C-1046 | PROJ-C | Improvement - performance issue 46 | Improvement | Highest | In Progress | Hiro | Reporter3 | 2025-02-16 |  | 5 | UI | performance |  | Sprint 4 | 10 | 66.88
PROJ-C-1047 | PROJ-C | Story - dashboard issue 47 | Story | Lowest | Done | Emma | Reporter5 | 2024-02-11 | 2024-03-30 | 5 | Integration | hotfix |  | Sprint 8 | 1 | 37.6
PROJ-B-1048 | PROJ-B | Task - import issue 48 | Task | High | Done | Fahad | Reporter4 | 2025-05-22 | 2025-06-09 | 8 | UI | refactor | EPIC-25 | Sprint 9 | 0 | 52.61
PROJ-C-1049 | PROJ-C | Story - API issue 49 | Story | Low | In Progress | Jatin | Reporter4 | 2025-03-28 |  | 3 | Integration | research |  | Sprint 1 | 10 | 48.71
PROJ-A-1050 | PROJ-A | Story - payment issue 50 | Story | Medium | To Do | Gita | Reporter1 | 2024-08-18 |  | 5 | UI |  |  |  | 8 | 56.43
PROJ-B-1051 | PROJ-B | Improvement - dashboard issue 51 | Improvement | Highest | To Do | Isha | Reporter2 | 2025-01-27 | 2025-03-06 | 1 | API |  |  | Sprint 9 | 4 | 65.64
PROJ-B-1052 | PROJ-B | Story - export issue 52 | Story | High | In Review | Unassigned | Reporter4 | 2024-06-01 | 2024-07-01 | 3 | Integration |  | EPIC-30 | Sprint 4 | 11 | 19.1
PROJ-B-1053 | PROJ-B | Bug - dashboard issue 53 | Bug | High | To Do | Hiro | Reporter4 | 2025-01-30 |  |  | DB |  | EPIC-19 | Sprint 2 | 7 | 7.98
PROJ-B-1054 | PROJ-B | Bug - sync issue 54 | Bug | Low | Done | Carlos | Reporter1 | 2025-04-25 | 2025-06-14 |  | API | backend |  |  | 8 | 30.4
PROJ-B-1055 | PROJ-B | Story - sync issue 55 | Story | High | In Progress | Isha | Reporter1 | 2024-03-11 | 2024-04-23 | 2 | Docs |  |  |  | 1 | 35.49
PROJ-C-1056 | PROJ-C | Task - API issue 56 | Task | Lowest | In Progress | Alice | Reporter3 | 2025-01-02 | 2025-01-11 | 8 | DB |  | EPIC-3 | Sprint 7 | 9 | 54.65
PROJ-B-1057 | PROJ-B | Improvement - performance issue 57 | Improvement | Low | In Progress | Emma | Reporter4 | 2024-09-18 |  | 3 | Docs |  |  | Sprint 10 | 4 | 51.12
PROJ-B-1058 | PROJ-B | Story - export issue 58 | Story | Medium | In Progress | Gita | Reporter4 | 2024-04-19 | 2024-05-25 | 8 | API |  | EPIC-27 | Sprint 5 | 0 | 45.27
PROJ-C-1059 | PROJ-C | Epic - export issue 59 | Epic | Highest | Blocked | Hiro | Reporter3 | 2024-08-23 |  |  | Backend | refactor,performance |  |  | 12 | 52.73
PROJ-A-1060 | PROJ-A | Story - dashboard issue 60 | Story | Highest | In Review | Emma | Reporter4 | 2024-02-04 |  | 1 | API | hotfix | EPIC-26 | Sprint 6 | 8 | 40.14
PROJ-B-1061 | PROJ-B | Improvement - payment issue 61 | Improvement | Medium | Done | Hiro | Reporter3 | 2024-12-12 | 2025-02-01 | 5 | UI |  |  |  | 6 | 77.38
PROJ-C-1062 | PROJ-C | Task - sync issue 62 | Task | High | To Do | Isha | Reporter1 | 2025-04-10 | 2025-05-27 | 8 | DB |  |  | Sprint 4 | 7 | 2
PROJ-C-1063 | PROJ-C | Task - payment issue 63 | Task | High | In Review | Unassigned | Reporter4 | 2024-11-05 |  | 2 | UI |  | EPIC-16 | Sprint 4 | 8 | 10.85
PROJ-B-1064 | PROJ-B | Task - payment issue 64 | Task | Highest | In Review | Isha | Reporter4 | 2024-06-07 |  | 5 | Integration | frontend |  | Sprint 8 | 3 | 68.44
PROJ-A-1065 | PROJ-A | Sub-task - payment issue 65 | Sub-task | Medium | Blocked | Unassigned | Reporter3 | 2024-03-03 | 2024-03-15 |  | CI/CD |  | EPIC-7 | Sprint 10 | 0 | 4.05
PROJ-B-1066 | PROJ-B | Bug - API issue 66 | Bug | Low | In Review | Bob | Reporter5 | 2024-07-31 |  |  | API |  |  | Sprint 5 | 2 | 79
PROJ-C-1067 | PROJ-C | Task - API issue 67 | Task | Medium | In Review | Alice | Reporter2 | 2024-01-16 | 2024-03-06 | 8 | API | frontend | EPIC-14 | Sprint 12 | 1 | 38.1
PROJ-B-1068 | PROJ-B | Story - login issue 68 | Story | Low | In Progress | Jatin | Reporter1 | 2025-06-17 | 2025-07-28 | 1 | DB |  |  | Sprint 12 | 7 | 5.88
PROJ-A-1069 | PROJ-A | Task - import issue 69 | Task | Low | To Do | Jatin | Reporter5 | 2025-07-15 |  | 8 | Integration | security,frontend |  | Sprint 11 | 10 | 70.22
PROJ-C-1070 | PROJ-C | Story - import issue 70 | Story | Medium | In Progress | Divya | Reporter4 | 2024-12-13 |  | 5 | Docs | performance |  | Sprint 3 | 10 | 73.84
PROJ-A-1071 | PROJ-A | Bug - export issue 71 | Bug | Low | In Progress | Fahad | Reporter2 | 2025-07-23 | 2025-08-27 |  | Docs | security |  |  | 4 | 48.03
PROJ-B-1072 | PROJ-B | Bug - export issue 72 | Bug | Medium | To Do | Hiro | Reporter2 | 2024-04-20 | 2024-05-25 |  | UI |  |  |  | 8 | 77.96
PROJ-C-1073 | PROJ-C | Story - sync issue 73 | Story | High | To Do | Unassigned | Reporter3 | 2024-01-30 | 2024-03-14 | 3 | API |  |  | Sprint 3 | 11 | 50.65
PROJ-A-1074 | PROJ-A | Bug - export issue 74 | Bug | Medium | In Progress | Hiro | Reporter3 | 2024-06-10 | 2024-07-26 |  | CI/CD |  |  |  | 2 | 12.59
PROJ-C-1075 | PROJ-C | Bug - payment issue 75 | Bug | Low | In Progress | Gita | Reporter4 | 2025-03-28 | 2025-04-10 |  | API | research |  | Sprint 4 | 6 | 78.76
PROJ-A-1076 | PROJ-A | Bug - performance issue 76 | Bug | Medium | To Do | Carlos | Reporter3 | 2024-10-23 | 2024-10-23 |  | Docs |  | EPIC-23 | Sprint 9 | 10 | 64.5
PROJ-A-1077 | PROJ-A | Task - import issue 77 | Task | High | In Progress | Hiro | Reporter1 | 2024-11-16 |  | 13 | Docs |  |  |  | 2 | 64.11
PROJ-C-1078 | PROJ-C | Story - payment issue 78 | Story | High | In Progress | Gita | Reporter1 | 2024-09-06 | 2024-10-01 | 5 | CI/CD | release | EPIC-6 | Sprint 11 | 1 | 42.45
PROJ-A-1079 | PROJ-A | Improvement - dashboard issue 79 | Improvement | Medium | Done | Unassigned | Reporter2 | 2024-08-29 | 2024-09-04 | 3 | Backend |  |  | Sprint 3 | 12 | 50.24
PROJ-B-1080 | PROJ-B | Epic - export issue 80 | Epic | High | In Progress | Jatin | Reporter5 | 2024-11-26 |  |  | Backend | research |  | Sprint 5 | 9 | 4.49
PROJ-C-1081 | PROJ-C | Bug - payment issue 81 | Bug | Medium | To Do | Fahad | Reporter3 | 2024-03-19 |  |  | Integration | research |  |  | 11 | 71.67
PROJ-B-1082 | PROJ-B | Improvement - performance issue 82 | Improvement | Medium | To Do | Jatin | Reporter4 | 2025-05-28 | 2025-05-31 | 1 | CI/CD |  | EPIC-23 | Sprint 11 | 2 | 3.13
PROJ-C-1083 | PROJ-C | Task - import issue 83 | Task | Medium | In Progress | Carlos | Reporter3 | 2025-01-16 |  | 5 | CI/CD | frontend,security |  | Sprint 6 | 1 | 44.64
PROJ-B-1084 | PROJ-B | Task - dashboard issue 84 | Task | High | In Review | Jatin | Reporter2 | 2024-12-07 | 2025-01-18 | 3 | API |  |  | Sprint 10 | 11 | 75.04
PROJ-B-1085 | PROJ-B | Story - import issue 85 | Story | High | In Progress | Carlos | Reporter5 | 2024-04-05 |  | 8 | API | hotfix |  | Sprint 8 | 3 | 18.12
PROJ-A-1086 | PROJ-A | Bug - export issue 86 | Bug | Medium | Done | Isha | Reporter5 | 2025-06-23 | 2025-06-25 |  | CI/CD | security,backend | EPIC-27 | Sprint 10 | 12 | 72.21
PROJ-C-1087 | PROJ-C | Task - performance issue 87 | Task | Medium | In Review | Divya | Reporter4 | 2024-10-18 |  | 2 | Integration | release | EPIC-19 |  | 7 | 61.56
PROJ-B-1088 | PROJ-B | Story - login issue 88 | Story | Medium | To Do | Divya | Reporter5 | 2024-05-21 |  | 13 | DB |  |  | Sprint 9 | 1 | 22.81
PROJ-A-1089 | PROJ-A | Task - export issue 89 | Task | Highest | To Do | Gita | Reporter1 | 2024-08-15 |  | 1 | DB | performance,backend | EPIC-3 | Sprint 1 | 5 | 74.47
PROJ-C-1090 | PROJ-C | Story - performance issue 90 | Story | High | To Do | Emma | Reporter4 | 2024-05-22 |  | 5 | Integration |  | EPIC-7 |  | 8 | 75.22
PROJ-C-1091 | PROJ-C | Story - performance issue 91 | Story | Low | To Do | Emma | Reporter1 | 2024-02-18 | 2024-03-29 | 1 | UI |  |  | Sprint 11 | 8 | 46
PROJ-C-1092 | PROJ-C | Bug - payment issue 92 | Bug | Medium | In Review | Divya | Reporter5 | 2025-03-02 | 2025-04-13 |  | Integration |  | EPIC-17 | Sprint 9 | 8 | 1.63
PROJ-B-1093 | PROJ-B | Bug - payment issue 93 | Bug | Medium | In Progress | Alice | Reporter3 | 2024-03-10 | 2024-04-25 |  | CI/CD | hotfix | EPIC-18 | Sprint 11 | 2 | 66.43
PROJ-C-1094 | PROJ-C | Story - login issue 94 | Story | High | In Review | Carlos | Reporter1 | 2025-04-13 | 2025-04-25 | 2 | UI | security |  | Sprint 5 | 0 | 60.26
PROJ-A-1095 | PROJ-A | Task - import issue 95 | Task | High | To Do | Unassigned | Reporter3 | 2024-10-06 | 2024-10-29 | 5 | Docs | performance |  | Sprint 8 | 5 | 73.94
PROJ-C-1096 | PROJ-C | Task - payment issue 96 | Task | Low | In Progress | Gita | Reporter5 | 2024-07-03 | 2024-07-23 | 1 | API | research |  | Sprint 12 | 7 | 28.12
PROJ-A-1097 | PROJ-A | Story - import issue 97 | Story | Highest | In Review | Gita | Reporter3 | 2024-02-28 | 2024-04-08 | 3 | Integration |  |  |  | 2 | 67.89
PROJ-C-1098 | PROJ-C | Epic - login issue 98 | Epic | Lowest | To Do | Unassigned | Reporter3 | 2025-01-05 | 2025-02-10 |  | Integration | performance |  | Sprint 2 | 9 | 11.02
PROJ-B-1099 | PROJ-B | Task - payment issue 99 | Task | High | To Do | Bob | Reporter1 | 2024-07-09 | 2024-08-02 | 3 | CI/CD | release |  | Sprint 8 | 3 | 9.81
PROJ-A-1100 | PROJ-A | Story - sync issue 100 | Story | High | In Progress | Bob | Reporter3 | 2024-12-21 |  | 3 | CI/CD | hotfix,security | EPIC-8 | Sprint 4 | 12 | 11.11
PROJ-B-1101 | PROJ-B | Bug - performance issue 101 | Bug | Medium | In Progress | Isha | Reporter2 | 2024-03-29 | 2024-04-23 |  | Integration | backend | EPIC-11 | Sprint 8 | 7 | 54.41
PROJ-B-1102 | PROJ-B | Bug - login issue 102 | Bug | High | In Review | Jatin | Reporter2 | 2024-05-12 | 2024-07-09 |  | CI/CD |  | EPIC-6 | Sprint 12 | 3 | 27.68
PROJ-C-1103 | PROJ-C | Improvement - payment issue 103 | Improvement | High | To Do | Unassigned | Reporter5 | 2024-10-08 | 2024-10-27 | 8 | Docs | hotfix,backend |  |  | 9 | 27.01
PROJ-C-1104 | PROJ-C | Bug - import issue 104 | Bug | High | To Do | Unassigned | Reporter5 | 2024-09-28 |  |  | Integration | refactor |  | Sprint 4 | 12 | 64.59
PROJ-B-1105 | PROJ-B | Task - dashboard issue 105 | Task | Low | To Do | Hiro | Reporter4 | 2025-05-10 | 2025-05-31 | 3 | CI/CD |  |  |  | 6 | 10.46
PROJ-B-1106 | PROJ-B | Story - login issue 106 | Story | Low | To Do | Bob | Reporter3 | 2025-04-05 | 2025-04-11 | 3 | DB |  |  |  | 2 | 65.08
PROJ-C-1107 | PROJ-C | Story - performance issue 107 | Story | Medium | To Do | Isha | Reporter4 | 2025-05-25 |  | 1 | UI |  |  |  | 3 | 46.67
PROJ-A-1108 | PROJ-A | Bug - login issue 108 | Bug | Medium | Done | Unassigned | Reporter4 | 2024-10-19 | 2024-11-22 |  | CI/CD |  |  |  | 12 | 32.26
PROJ-A-1109 | PROJ-A | Task - sync issue 109 | Task | Medium | To Do | Isha | Reporter3 | 2024-03-16 | 2024-04-13 | 8 | Docs |  |  | Sprint 6 | 8 | 75.12
PROJ-A-1110 | PROJ-A | Bug - performance issue 110 | Bug | Medium | In Progress | Alice | Reporter1 | 2024-05-20 |  |  | Integration | hotfix,research |  | Sprint 7 | 9 | 59.15
PROJ-B-1111 | PROJ-B | Story - export issue 111 | Story | Medium | In Progress | Hiro | Reporter5 | 2024-11-02 | 2024-11-03 | 3 | Docs | refactor |  |  | 11 | 50.34
PROJ-C-1112 | PROJ-C | Story - login issue 112 | Story | Highest | Done | Jatin | Reporter5 | 2024-08-21 | 2024-10-06 | 8 | DB | security,backend |  | Sprint 10 | 11 | 8.79
PROJ-A-1113 | PROJ-A | Task - performance issue 113 | Task | Medium | In Progress | Divya | Reporter4 | 2025-05-28 |  | 13 | Docs |  |  | Sprint 11 | 7 | 42.04
PROJ-B-1114 | PROJ-B | Sub-task - API issue 114 | Sub-task | Medium | In Progress | Isha | Reporter3 | 2024-09-27 |  |  | Backend | release |  |  | 12 | 23.12
PROJ-A-1115 | PROJ-A | Story - import issue 115 | Story | Medium | In Progress | Isha | Reporter3 | 2024-10-21 | 2024-12-03 | 5 | CI/CD |  | EPIC-10 |  | 1 | 27.71
PROJ-B-1116 | PROJ-B | Story - dashboard issue 116 | Story | High | To Do | Isha | Reporter3 | 2025-07-29 |  | 1 | Integration |  | EPIC-2 | Sprint 9 | 3 | 51.04
PROJ-A-1117 | PROJ-A | Bug - dashboard issue 117 | Bug | Medium | In Progress | Unassigned | Reporter2 | 2024-01-06 |  |  | DB | research |  |  | 4 | 25.69
PROJ-C-1118 | PROJ-C | Bug - dashboard issue 118 | Bug | High | In Review | Divya | Reporter5 | 2024-02-08 |  |  | DB |  | EPIC-30 | Sprint 7 | 12 | 39.63
PROJ-C-1119 | PROJ-C | Sub-task - payment issue 119 | Sub-task | Highest | Done | Alice | Reporter3 | 2025-08-04 | 2025-09-11 |  | API | research,backend |  | Sprint 4 | 12 | 9.01
PROJ-A-1120 | PROJ-A | Story - API issue 120 | Story | High | Done | Alice | Reporter3 | 2024-10-29 | 2024-12-04 | 2 | Integration |  |  |  | 8 | 26.23
PROJ-B-1121 | PROJ-B | Story - performance issue 121 | Story | Medium | To Do | Fahad | Reporter2 | 2024-01-07 | 2024-01-22 | 3 | API | frontend,hotfix |  | Sprint 1 | 10 | 9.46
PROJ-B-1122 | PROJ-B | Bug - API issue 122 | Bug | High | Blocked | Emma | Reporter1 | 2024-10-29 | 2024-11-12 |  | Backend | performance |  | Sprint 8 | 12 | 43
PROJ-C-1123 | PROJ-C | Improvement - export issue 123 | Improvement | High | In Review | Jatin | Reporter1 | 2025-06-22 | 2025-08-06 | 1 | Integration | release,refactor |  | Sprint 9 | 7 | 9.3
PROJ-A-1124 | PROJ-A | Story - import issue 124 | Story | Medium | Done | Hiro | Reporter1 | 2025-04-09 | 2025-04-17 | 5 | Integration | refactor |  | Sprint 1 | 11 | 17.43
PROJ-A-1125 | PROJ-A | Bug - dashboard issue 125 | Bug | Medium | To Do | Alice | Reporter1 | 2025-04-28 | 2025-05-24 |  | CI/CD | security,hotfix |  | Sprint 7 | 6 | 6.42
PROJ-C-1126 | PROJ-C | Improvement - dashboard issue 126 | Improvement | Low | Done | Bob | Reporter2 | 2025-07-04 | 2025-07-29 | 13 | Backend |  |  |  | 7 | 53.88
PROJ-C-1127 | PROJ-C | Task - payment issue 127 | Task | Medium | To Do | Hiro | Reporter3 | 2024-06-07 | 2024-08-05 | 1 | CI/CD | frontend,backend | EPIC-4 | Sprint 8 | 9 | 53.76
PROJ-A-1128 | PROJ-A | Bug - API issue 128 | Bug | Lowest | In Progress | Isha | Reporter2 | 2024-02-27 | 2024-03-16 |  | CI/CD |  |  | Sprint 11 | 5 | 18.95
PROJ-A-1129 | PROJ-A | Sub-task - dashboard issue 129 | Sub-task | Medium | In Progress | Emma | Reporter1 | 2025-07-24 |  |  | Docs | research,frontend |  |  | 10 | 30.49
PROJ-C-1130 | PROJ-C | Task - API issue 130 | Task | Medium | To Do | Gita | Reporter2 | 2025-07-04 | 2025-08-27 | 3 | CI/CD |  |  |  | 8 | 33.01
PROJ-B-1131 | PROJ-B | Story - export issue 131 | Story | Low | To Do | Divya | Reporter3 | 2024-03-21 |  | 1 | Integration |  | EPIC-9 | Sprint 10 | 9 | 3.16
PROJ-A-1132 | PROJ-A | Bug - export issue 132 | Bug | High | Done | Isha | Reporter2 | 2025-05-05 | 2025-05-18 |  | API |  | EPIC-30 | Sprint 12 | 1 | 59.75
PROJ-B-1133 | PROJ-B | Improvement - sync issue 133 | Improvement | High | Done | Gita | Reporter2 | 2025-07-19 | 2025-08-08 | 5 | DB | refactor | EPIC-17 |  | 7 | 7.89
PROJ-C-1134 | PROJ-C | Story - API issue 134 | Story | High | Blocked | Fahad | Reporter3 | 2025-02-27 | 2025-04-23 | 13 | Backend | security,hotfix | EPIC-11 | Sprint 10 | 3 | 39.94
PROJ-C-1135 | PROJ-C | Sub-task - export issue 135 | Sub-task | Medium | Done | Hiro | Reporter4 | 2025-04-16 | 2025-04-26 |  | Backend | research,backend |  | Sprint 11 | 0 | 41.92
PROJ-A-1136 | PROJ-A | Sub-task - dashboard issue 136 | Sub-task | High | Done | Gita | Reporter2 | 2024-08-24 | 2024-08-28 |  | UI | performance | EPIC-21 | Sprint 10 | 7 | 52.74
PROJ-A-1137 | PROJ-A | Bug - login issue 137 | Bug | Medium | To Do | Isha | Reporter3 | 2025-07-02 |  |  | Integration |  |  |  | 2 | 8.56
PROJ-A-1138 | PROJ-A | Story - payment issue 138 | Story | Medium | In Review | Emma | Reporter3 | 2024-09-30 |  | 3 | DB |  |  | Sprint 11 | 1 | 52.3
PROJ-C-1139 | PROJ-C | Epic - dashboard issue 139 | Epic | Low | In Progress | Isha | Reporter4 | 2024-02-27 |  |  | UI | performance |  | Sprint 2 | 8 | 73.53
PROJ-A-1140 | PROJ-A | Bug - payment issue 140 | Bug | High | Done | Hiro | Reporter3 | 2024-02-17 | 2024-04-16 |  | Docs |  |  | Sprint 1 | 2 | 74.3
PROJ-B-1141 | PROJ-B | Bug - import issue 141 | Bug | Medium | To Do | Gita | Reporter1 | 2024-11-02 | 2024-11-17 |  | Docs |  | EPIC-25 |  | 12 | 79.08
PROJ-C-1142 | PROJ-C | Bug - export issue 142 | Bug | High | In Progress | Bob | Reporter4 | 2024-08-25 |  |  | Integration |  |  | Sprint 6 | 0 | 50.73
PROJ-B-1143 | PROJ-B | Story - payment issue 143 | Story | Medium | Blocked | Gita | Reporter2 | 2025-08-22 |  | 8 | API |  |  | Sprint 3 | 6 | 56.93
PROJ-C-1144 | PROJ-C | Bug - sync issue 144 | Bug | Medium | In Progress | Bob | Reporter1 | 2024-11-11 | 2024-12-29 |  | UI |  |  | Sprint 9 | 6 | 8.26
PROJ-A-1145 | PROJ-A | Task - payment issue 145 | Task | Low | In Review | Fahad | Reporter4 | 2024-01-13 | 2024-02-06 | 13 | Integration |  |  | Sprint 3 | 10 | 30.46
PROJ-A-1146 | PROJ-A | Task - payment issue 146 | Task | Medium | To Do | Carlos | Reporter4 | 2024-10-09 | 2024-11-08 | 3 | API |  |  | Sprint 10 | 3 | 36.63
PROJ-A-1147 | PROJ-A | Task - dashboard issue 147 | Task | Highest | In Progress | Jatin | Reporter4 | 2024-12-03 | 2024-12-30 | 3 | API | release,research | EPIC-13 |  | 4 | 58.79
PROJ-C-1148 | PROJ-C | Story - API issue 148 | Story | Medium | To Do | Gita | Reporter3 | 2025-02-06 | 2025-04-06 | 8 | Integration | frontend,performance |  |  | 7 | 63.81
PROJ-C-1149 | PROJ-C | Bug - sync issue 149 | Bug | High | Done | Unassigned | Reporter4 | 2024-05-22 | 2024-07-01 |  | Backend |  |  |  | 1 | 35.93
PROJ-C-1150 | PROJ-C | Story - export issue 150 | Story | Medium | In Progress | Gita | Reporter5 | 2024-02-07 |  | 13 | CI/CD | backend,frontend |  | Sprint 6 | 2 | 51.76
PROJ-A-1151 | PROJ-A | Story - API issue 151 | Story | High | In Review | Fahad | Reporter4 | 2024-04-18 | 2024-05-04 | 8 | Docs | release,research | EPIC-15 |  | 9 | 55.23
PROJ-A-1152 | PROJ-A | Task - dashboard issue 152 | Task | Lowest | To Do | Gita | Reporter1 | 2024-04-28 |  | 3 | API |  |  | Sprint 2 | 7 | 57.76
PROJ-B-1153 | PROJ-B | Task - payment issue 153 | Task | Medium | Done | Bob | Reporter1 | 2024-12-17 | 2025-01-27 | 13 | CI/CD | release,refactor | EPIC-6 | Sprint 7 | 7 | 18.55
PROJ-B-1154 | PROJ-B | Story - import issue 154 | Story | Medium | In Review | Gita | Reporter1 | 2024-07-21 | 2024-08-17 | 1 | Docs | backend |  |  | 8 | 14.96
PROJ-B-1155 | PROJ-B | Bug - import issue 155 | Bug | Low | In Review | Hiro | Reporter5 | 2024-11-16 |  |  | Integration | research |  |  | 11 | 64.05
PROJ-C-1156 | PROJ-C | Story - dashboard issue 156 | Story | High | In Progress | Divya | Reporter3 | 2024-04-29 | 2024-06-12 | 8 | DB |  |  | Sprint 8 | 10 | 42.99
PROJ-C-1157 | PROJ-C | Sub-task - login issue 157 | Sub-task | Medium | To Do | Emma | Reporter2 | 2024-07-10 | 2024-08-07 |  | CI/CD |  |  | Sprint 7 | 8 | 40.44
PROJ-B-1158 | PROJ-B | Task - login issue 158 | Task | Medium | Done | Hiro | Reporter4 | 2024-06-20 | 2024-06-25 | 2 | API |  |  | Sprint 8 | 9 | 59.4
PROJ-B-1159 | PROJ-B | Story - login issue 159 | Story | Low | To Do | Isha | Reporter3 | 2025-07-09 |  | 13 | DB | backend |  | Sprint 4 | 4 | 69.98
PROJ-A-1160 | PROJ-A | Task - export issue 160 | Task | Medium | Done | Hiro | Reporter1 | 2024-08-30 | 2024-09-12 | 13 | Integration |  |  |  | 3 | 64.44
PROJ-C-1161 | PROJ-C | Task - payment issue 161 | Task | Medium | In Progress | Fahad | Reporter3 | 2024-10-23 |  | 2 | CI/CD |  |  |  | 10 | 10.15
PROJ-A-1162 | PROJ-A | Bug - sync issue 162 | Bug | High | Done | Unassigned | Reporter4 | 2025-05-16 | 2025-05-25 |  | Docs | backend |  |  | 1 | 32.23
PROJ-C-1163 | PROJ-C | Task - payment issue 163 | Task | Highest | In Progress | Hiro | Reporter3 | 2025-08-18 | 2025-10-06 | 13 | DB | performance,security | EPIC-18 | Sprint 7 | 3 | 39.58
PROJ-B-1164 | PROJ-B | Improvement - login issue 164 | Improvement | Medium | In Review | Jatin | Reporter4 | 2024-12-17 |  | 1 | UI | frontend | EPIC-28 | Sprint 8 | 0 | 79.35
PROJ-B-1165 | PROJ-B | Bug - sync issue 165 | Bug | High | To Do | Unassigned | Reporter3 | 2024-06-11 |  |  | UI | backend | EPIC-29 | Sprint 1 | 6 | 50.05
PROJ-C-1166 | PROJ-C | Story - API issue 166 | Story | Medium | In Review | Bob | Reporter1 | 2024-08-06 | 2024-08-14 | 8 | Docs |  |  |  | 6 | 55.52
PROJ-B-1167 | PROJ-B | Bug - sync issue 167 | Bug | Medium | Done | Bob | Reporter1 | 2024-11-16 | 2024-12-09 |  | Backend |  |  | Sprint 2 | 8 | 45.06
PROJ-C-1168 | PROJ-C | Story - performance issue 168 | Story | Medium | Done | Unassigned | Reporter2 | 2025-02-25 | 2025-04-05 | 2 | UI |  | EPIC-4 | Sprint 7 | 5 | 77.06
PROJ-B-1169 | PROJ-B | Epic - login issue 169 | Epic | Medium | In Review | Divya | Reporter5 | 2024-10-18 |  |  | CI/CD |  |  |  | 3 | 41.42
PROJ-C-1170 | PROJ-C | Bug - payment issue 170 | Bug | Medium | In Review | Divya | Reporter4 | 2025-01-30 | 2025-03-02 |  | Integration |  | EPIC-12 |  | 2 | 30.95
PROJ-C-1171 | PROJ-C | Task - login issue 171 | Task | Medium | To Do | Hiro | Reporter1 | 2024-01-18 |  | 3 | Backend |  |  | Sprint 5 | 10 | 57.01
PROJ-B-1172 | PROJ-B | Task - payment issue 172 | Task | Medium | In Review | Isha | Reporter5 | 2024-06-05 | 2024-06-24 | 8 | Backend |  | EPIC-11 | Sprint 11 | 12 | 66.76
PROJ-C-1173 | PROJ-C | Story - payment issue 173 | Story | Medium | In Progress | Divya | Reporter1 | 2024-09-07 | 2024-10-04 | 5 | Integration | hotfix | EPIC-23 | Sprint 1 | 2 | 39.71
PROJ-B-1174 | PROJ-B | Story - sync issue 174 | Story | High | Done | Carlos | Reporter3 | 2024-05-09 | 2024-06-25 | 13 | UI |  | EPIC-26 | Sprint 9 | 1 | 21.04
PROJ-C-1175 | PROJ-C | Story - sync issue 175 | Story | Medium | In Progress | Alice | Reporter4 | 2025-08-03 | 2025-08-13 | 1 | Integration |  | EPIC-17 | Sprint 1 | 3 | 3.68
PROJ-B-1176 | PROJ-B | Task - import issue 176 | Task | Medium | Blocked | Alice | Reporter5 | 2025-03-05 | 2025-03-20 | 13 | API |  |  | Sprint 11 | 0 | 14.35
PROJ-C-1177 | PROJ-C | Sub-task - performance issue 177 | Sub-task | Highest | To Do | Hiro | Reporter3 | 2024-11-14 | 2024-12-19 |  | UI | refactor |  | Sprint 6 | 9 | 77.75
PROJ-A-1178 | PROJ-A | Story - API issue 178 | Story | Medium | Done | Carlos | Reporter1 | 2025-02-23 | 2025-02-24 | 8 | API | frontend,hotfix | EPIC-22 | Sprint 12 | 11 | 24.6
PROJ-A-1179 | PROJ-A | Story - API issue 179 | Story | Medium | In Progress | Alice | Reporter2 | 2024-10-13 | 2024-12-10 | 8 | DB |  | EPIC-24 | Sprint 2 | 8 | 10.68
PROJ-B-1180 | PROJ-B | Bug - import issue 180 | Bug | Medium | In Progress | Carlos | Reporter2 | 2024-10-25 | 2024-11-14 |  | Docs |  | EPIC-15 | Sprint 2 | 3 | 10.89
PROJ-C-1181 | PROJ-C | Bug - API issue 181 | Bug | Low | In Progress | Fahad | Reporter4 | 2024-05-03 | 2024-06-21 |  | DB | backend | EPIC-26 | Sprint 12 | 11 | 48.26
PROJ-A-1182 | PROJ-A | Improvement - sync issue 182 | Improvement | Medium | To Do | Divya | Reporter3 | 2025-02-09 | 2025-03-24 | 3 | CI/CD |  | EPIC-13 |  | 8 | 59.85
PROJ-A-1183 | PROJ-A | Bug - API issue 183 | Bug | Low | Done | Bob | Reporter1 | 2024-03-04 | 2024-04-26 |  | Backend | performance |  |  | 1 | 46.59
PROJ-B-1184 | PROJ-B | Improvement - export issue 184 | Improvement | Low | Reopened | Divya | Reporter4 | 2024-05-11 | 2024-07-04 | 1 | UI |  | EPIC-30 | Sprint 12 | 6 | 39.69
PROJ-B-1185 | PROJ-B | Story - login issue 185 | Story | Medium | To Do | Carlos | Reporter3 | 2024-10-13 | 2024-10-22 | 8 | Integration | refactor,release |  | Sprint 1 | 1 | 22.38
PROJ-A-1186 | PROJ-A | Task - export issue 186 | Task | High | Done | Divya | Reporter5 | 2024-01-20 | 2024-02-13 | 5 | Integration |  | EPIC-19 | Sprint 7 | 4 | 14.39
PROJ-B-1187 | PROJ-B | Story - export issue 187 | Story | Lowest | Done | Emma | Reporter1 | 2025-04-28 | 2025-05-31 | 8 | Backend |  | EPIC-22 | Sprint 9 | 12 | 73.38
PROJ-A-1188 | PROJ-A | Epic - export issue 188 | Epic | Highest | In Review | Gita | Reporter3 | 2024-06-26 | 2024-08-02 |  | CI/CD |  |  | Sprint 10 | 0 | 56.28
PROJ-B-1189 | PROJ-B | Sub-task - login issue 189 | Sub-task | Medium | In Review | Divya | Reporter4 | 2025-07-09 | 2025-08-09 |  | UI | release,frontend |  | Sprint 10 | 3 | 64.52
PROJ-B-1190 | PROJ-B | Story - dashboard issue 190 | Story | Highest | Done | Fahad | Reporter1 | 2024-01-23 | 2024-02-01 | 1 | CI/CD | backend | EPIC-22 | Sprint 2 | 5 | 24.14
PROJ-A-1191 | PROJ-A | Sub-task - export issue 191 | Sub-task | High | In Progress | Unassigned | Reporter4 | 2024-11-20 | 2024-12-25 |  | Backend |  | EPIC-24 | Sprint 3 | 2 | 58.31
PROJ-C-1192 | PROJ-C | Sub-task - API issue 192 | Sub-task | Medium | Reopened | Jatin | Reporter1 | 2024-07-05 |  |  | Docs | hotfix | EPIC-3 | Sprint 6 | 2 | 50.89
PROJ-A-1193 | PROJ-A | Improvement - API issue 193 | Improvement | High | Done | Fahad | Reporter4 | 2024-01-12 | 2024-01-28 | 2 | Docs | backend |  | Sprint 8 | 11 | 33.57
PROJ-A-1194 | PROJ-A | Improvement - API issue 194 | Improvement | Medium | In Progress | Isha | Reporter4 | 2024-04-13 |  | 2 | DB |  | EPIC-11 | Sprint 2 | 1 | 27.34
PROJ-B-1195 | PROJ-B | Bug - import issue 195 | Bug | Low | Blocked | Bob | Reporter3 | 2025-05-09 |  |  | Docs | hotfix | EPIC-11 | Sprint 4 | 6 | 55.78
PROJ-C-1196 | PROJ-C | Sub-task - performance issue 196 | Sub-task | Medium | In Review | Emma | Reporter2 | 2024-04-08 | 2024-05-14 |  | Backend |  |  | Sprint 11 | 10 | 48.02
PROJ-A-1197 | PROJ-A | Bug - performance issue 197 | Bug | Medium | In Review | Bob | Reporter4 | 2024-04-28 | 2024-05-23 |  | DB |  | EPIC-21 | Sprint 3 | 5 | 70.84
PROJ-B-1198 | PROJ-B | Bug - dashboard issue 198 | Bug | Lowest | In Progress | Emma | Reporter2 | 2024-10-02 |  |  | CI/CD |  | EPIC-12 |  | 6 | 77.66
PROJ-C-1199 | PROJ-C | Bug - performance issue 199 | Bug | Low | In Progress | Isha | Reporter4 | 2025-07-02 |  |  | Integration |  |  | Sprint 12 | 0 | 40.17
PROJ-C-1200 | PROJ-C | Improvement - dashboard issue 200 | Improvement | High | In Review | Bob | Reporter4 | 2024-06-26 |  | 2 | CI/CD |  |  |  | 6 | 16.15